## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
1 | TA Profile Creation | As a TA, I want to create an applicant profile and upload my CV, so that MOs can view my qualifications. | 1 | 1 | 1. TA can input basic personal information. 2. TA can upload a CV. 3. Profile data is saved in a local text/CSV file. | 3 | Must use plain text format. No database allowed. | 2026-03-09 | 2026-03-22
2 | MO Job Posting | As a Module Organiser, I want to post new TA job openings, so that TAs can find and apply for them. | 1 | 1 | 1. MO can enter specific job details. 2. Job opening is appended to a central JSON/XML file. | 3 | Ensure interoperability with text formats. | 2026-03-09 | 2026-03-22
3 | TA Job Application | As a TA, I want to view available jobs and apply for them, so that I can secure a TA position. | 2 | 1 | 1. TA can view a list of all open jobs. 2. TA can click apply for a specific job. 3. Application record is saved locally. | 5 | Link TA profile data with Job ID using simple text records. | 2026-03-16 | 2026-03-22
4 | MO Applicant Selection | As an MO, I want to review applicants and select TAs for my module, so that I can build my teaching team. | 2 | 2 | 1. MO can view a list of applicants for their job. 2. MO can change applicant status to accepted or rejected. 3. Status update is saved to the system. | 5 | Needs simple UI to list applicants parsed from text files. | 2026-03-23 | 2026-04-12
5 | Admin Workload Dashboard | As an Admin, I want to check the overall workload of all TAs, so that I can ensure workload is balanced. | 3 | 2 | 1. Admin can view a summary of assigned hours for all TAs. 2. System visually highlights TAs exceeding the maximum allowed hours. | 3 | Calculate total hours from all text files. | 2026-03-23 | 2026-04-12
6 | AI Skill Matching | As an MO, I want the system to match TA skills with my job requirements using AI, so that I can find the best fit quickly. | 4 | 3 | 1. System calculates a match score between TA CV and job description. 2. System provides an explainable reason for the generated score. | 8 | AI results must not be blindly accepted; must provide explanation. | 2026-04-13 | 2026-05-03
7 | AI Skill Gap Analysis | As a TA, I want to use AI to identify missing skills for a desired job, so that I know what to improve. | 5 | 4 | 1. System identifies missing skills by comparing CV and job description. 2. System outputs a list of missing keywords with reasoning. | 5 | Integrate responsibly and critically. | 2026-05-04 | 2026-05-24